## Sprint 1 Gantt Chart
QalaBazaar — Sprint 1 Gantt Chart (Aug 18–29, 2026)
Task | Assigned To | Priority | Start Date | End Date | Duration (days)
Set up Trello board | Sandhya Dahal | High | 2026-08-18 | 2026-08-18 | 1
Set up GitHub repository & folders | Sandhya Dahal | High | 2026-08-18 | 2026-08-17 | 0
Draft functional requirements | Sandhya Dahal | High | 2026-08-19 | 2026-08-19 | 1
Draft non-functional requirements | Sandhya Dahal | High | 2026-08-20 | 2026-08-19 | 0
Conduct stakeholder analysis | Bandana Pandey | High | 2026-08-20 | 2026-08-19 | 0
Create Use Case Diagram | Bandana Pandey | High | 2026-08-16 | 2026-08-17 | 2
Create Class Diagram | Bandana Pandey | High | 2026-08-17 | 2026-08-17 | 1
Create Sequence & Activity Diagrams | Bandana Pandey | High | 2026-08-17 | 2026-08-18 | 2
Design test cases (Unit/Integration/System/UAT) | Both | Medium | 2026-08-18 | 2026-08-18 | 1
Create branch, commit, open & merge PR | Sandhya Dahal | High | 2026-08-17 | 2026-08-19 | 3
Sprint review & retrospective | Both | High | 2026-08-17 | 2026-08-19 | 3