## Unit Testing
QalaBazaar E-commerce Platform (QMS) - Unit Testing
Test Case ID | Related Requirement | Scenario Type | Test Objective | Preconditions | Test Input | Test Steps | Expected Output | Actual Output | Status | Tester | Date Tested
UT-01 | FR1 | Positive | Verify the Customer Registration function accepts a complete, valid customer record. | Registration form is open and empty; user not logged in. | Name: Sunita Shrestha; Email: sunita@example.com; Phone: 9841022334; Password: Valid123! | 1) Enter all required fields with valid data. 2) Click 'Register'. | Account is created; system generates a unique Customer ID (e.g., KB-C-1001) and shows a confirmation message. | Account created; Customer ID KB-C-1001 generated; confirmation shown as expected. | Pass | S. Dahal (Dev) | 2026-08-10
UT-02 | FR1 | Negative | Verify registration is blocked when a mandatory field (Email) is left blank. | Registration form is open and empty. | Name: Ram Thapa; Email: (blank); Password: Valid123! | 1) Leave Email blank. 2) Fill remaining fields. 3) Click 'Register'. | Registration is blocked; validation message 'Email is required' is displayed. | Registration blocked; correct validation message shown. | Pass | S. Dahal (Dev) | 2026-08-10
UT-03 | FR1 | Negative | Verify the password field rejects a weak password that does not meet complexity rules. | Registration form is open. | Password: '1234' | 1) Enter a weak password. 2) Click 'Register'. | Registration is blocked; message 'Password must be at least 8 characters and include a number' is shown. | Registration proceeded without a validation error; weak password was accepted and stored. | Fail | S. Dahal (Dev) | 2026-08-10
UT-04 | FR11 | Positive | Verify a registered user can log in with correct credentials. | User account 'sunita_s' exists with a known valid password. | Username: sunita_s; Password: (valid) | 1) Enter valid username/password. 2) Click 'Login'. | User is authenticated and redirected to their dashboard. | Login successful; dashboard loaded in 1.2 seconds. | Pass | S. Dahal (Dev) | 2026-08-10
UT-05 | FR11 | Negative | Verify login is rejected when an incorrect password is entered. | User account 'sunita_s' exists. | Username: sunita_s; Password: 'wrongPass1' | 1) Enter valid username, incorrect password. 2) Click 'Login'. | Login is rejected; message 'Invalid username or password' is shown. | Login rejected with the correct message displayed. | Pass | S. Dahal (Dev) | 2026-08-10
UT-06 | FR4 | Positive | Verify the stock-availability check function correctly reports an in-stock product. | Product 'Hand-woven Dhaka Scarf' has 5 units in stock. | Product ID: KB-P-2001; requested quantity: 1 | 1) Call the availability-check function for the given product/quantity. | Function returns Available = true. | Function returned Available = true, matching the expected result. | Pass | S. Dahal (Dev) | 2026-08-11
UT-07 | FR4 | Negative | Verify the stock-availability check function correctly blocks an out-of-stock product. | Product 'Ceramic Tea Set' has 0 units in stock. | Product ID: KB-P-2002; requested quantity: 1 | 1) Call the availability-check function for the given product/quantity. | Function returns Available = false with an 'Out of stock' flag. | Function returned Available = false; correct flag shown. | Pass | S. Dahal (Dev) | 2026-08-11
UT-08 | FR3 | Positive | Verify the product-search function returns the correct result for an exact product name match. | Product 'Hand-woven Dhaka Scarf' exists in the catalog. | Search term: 'Dhaka Scarf' | 1) Enter 'Dhaka Scarf' into the search field. 2) Press Enter. | At least one matching product for the Dhaka Scarf is displayed. | One matching product displayed correctly. | Pass | S. Dahal (Dev) | 2026-08-11
UT-09 | FR6 | Negative | Verify the payment function rejects a transaction when the payment gateway returns a declined response. | Cart total is Rs. 1,500; payment gateway configured to simulate a decline. | Card/payment details that trigger a simulated decline response | 1) Submit payment with the decline-triggering test details. | Payment is not completed; message 'Payment declined, please try again' is shown; order is not created. | Payment was marked as completed and an order was created despite the simulated decline response. | Fail | S. Dahal (Dev) | 2026-08-11
UT-10 | FR2 | Positive | Verify the add-product-listing function saves a new listing with all required fields. | Seller is logged in; product form is open and empty. | Name: 'Hand-carved Wooden Bowl'; Price: Rs. 850; Category: Home Decor; Stock: 10 | 1) Enter all required fields. 2) Click 'Add Product'. | Listing is saved and appears in the seller's product list with status 'Active'. | Listing saved and appeared correctly with status Active. | Pass | S. Dahal (Dev) | 2026-08-11

## Integration Testing
QalaBazaar E-commerce Platform (QMS) - Integration Testing
Test Case ID | Related Requirement | Scenario Type | Test Objective | Preconditions | Test Input | Test Steps | Expected Output | Actual Output | Status | Tester | Date Tested
IT-01 | FR1, FR2 | Positive | Verify a newly registered seller's account correctly flows into the Seller Dashboard module with permission to add products. | Registration and Seller Dashboard modules are connected to the staging database. | New seller 'Kiran Maharjan' registered via Registration module. | 1) Register Kiran Maharjan as a seller. 2) Open Seller Dashboard and check for 'Add Product' access. | Kiran Maharjan's account appears in Seller Dashboard with full add-product access. | Account appeared immediately with full access as expected. | Pass | B. Pandey (QA) | 2026-08-12
IT-02 | FR2, FR3 | Positive | Verify a product added by a seller appears correctly in the customer-facing Search/Browse module. | Seller and Search modules are both connected to the staging database. | Add product: 'Pashmina Shawl', Price Rs. 3,200, Category: Textiles. | 1) Add product via Seller module. 2) Open Search/Browse module and search for 'Pashmina Shawl'. | The new product appears in search results with correct price and category. | Product appeared correctly in search results. | Pass | B. Pandey (QA) | 2026-08-12
IT-03 | FR3 | Negative | Verify the Search module returns a 'No products found' message (not a system error) when a search term matches nothing. | No products named 'Xyzabc123' exist in the catalog. | Search term: 'Xyzabc123' | 1) Enter 'Xyzabc123' in the search box. 2) Press Enter. | System displays 'No products found' without crashing or throwing a system error. | Message displayed correctly; no crash. | Pass | B. Pandey (QA) | 2026-08-12
IT-04 | FR5, FR6 | Negative | Verify the Checkout module blocks payment when the cart is empty. | Customer is logged in; cart contains 0 items. | Attempt to proceed to checkout with an empty cart. | 1) Open Checkout with an empty cart. 2) Attempt to confirm payment. | Checkout is blocked; message 'Your cart is empty' is shown. | Checkout proceeded to the payment page despite the empty cart; no validation message appeared. | Fail | B. Pandey (QA) | 2026-08-12
IT-05 | FR5, FR6 | Positive | Verify a completed checkout correctly creates an order record and links to the Order Tracking module. | Customer has 2 items in cart; payment gateway sandbox is active. | Checkout: 2 items, total Rs. 2,750, payment via eSewa sandbox. | 1) Complete checkout and payment. 2) Open Order Tracking module for the customer. | New order appears in Order Tracking with status 'Placed' and correct item/amount details. | Order appeared correctly with status Placed and correct details. | Pass | B. Pandey (QA) | 2026-08-12
IT-06 | FR11, NFR1 | Positive | Verify that after logout, the session module correctly revokes access to protected modules. | User is logged in and has an active session. | User clicks 'Logout'. | 1) Click Logout. 2) Attempt to navigate back to the Order History page using the browser back button. | User is redirected to the login page; protected page is not accessible without re-authentication. | User redirected to login page; protected page inaccessible as expected. | Pass | B. Pandey (QA) | 2026-08-13
IT-07 | NFR1 | Negative | Verify a customer account is blocked from accessing the seller-only Product Management module. | Customer role does not have permission to manage products. | Customer attempts to open the Seller Dashboard's 'Manage Products' page directly via URL. | 1) Log in as customer. 2) Navigate directly to the Manage Products URL. | Access is denied; message 'You do not have permission to view this page' is shown. | Access denied with the correct message shown. | Pass | B. Pandey (QA) | 2026-08-13
IT-08 | FR4, FR6 | Positive | Verify the Inventory and Payment modules together prevent two customers from purchasing the last unit of a product simultaneously. | Product 'Silver Filigree Earrings' has exactly 1 unit in stock. | Two customers (Customer A, Customer B) simultaneously attempt to purchase the last unit. | 1) Customer A submits payment for the item. 2) Customer B submits payment for the same item moments later. | Only one purchase is confirmed; the second customer receives an 'Item no longer available' message and is not charged. | Only Customer A's purchase was confirmed; Customer B received the correct message and was not charged. | Pass | B. Pandey (QA) | 2026-08-13

## System Testing
QalaBazaar E-commerce Platform (QMS) - System Testing | [11 empty] | q
Test Case ID | Related Requirement | Scenario Type | Test Objective | Preconditions | Test Input | Test Steps | Expected Output | Actual Output | Status | Tester | Date Tested
ST-01 | FR1, FR2, FR3 | Positive | End-to-end: seller registers, lists a new product, and it is immediately retrievable via customer search. | Seller logged in; system running on staging environment. | New product 'Hand-painted Mithila Art', Price Rs. 1,800. | 1) Add product as seller. 2) Search for the product by name as a customer. 3) Open the returned listing. | Product listing succeeds; searching by name returns the product with all details matching input. | Listing and search both worked correctly; details matched. | Pass | B. Pandey (QA Lead) | 2026-08-13
ST-02 | FR5, FR6, FR7 | Positive | End-to-end: customer completes checkout and the order status updates in real time in Order Tracking. | Customer has items in cart; payment gateway sandbox accessible. | Checkout 2 items, total Rs. 2,100, payment via Khalti sandbox. | 1) Complete checkout. 2) Open Order Tracking view without logging out. | New order is visible in Order Tracking within a few seconds, with status 'Placed'. | Order appeared within 2 seconds of checkout with correct status. | Pass | B. Pandey (QA Lead) | 2026-08-13
ST-03 | FR4, FR6 | Negative | Verify the full system prevents overselling when two customers attempt to buy the last unit of a product concurrently. | Product 'Brass Singing Bowl' has exactly 1 unit in stock. | Two devices submit payment for the same last unit within the same second. | 1) Device A submits payment. 2) Device B submits payment for the identical item. | Only one purchase is saved; the other device receives a conflict message and is not charged. | Only Device A's purchase was saved; Device B received the conflict message as expected. | Pass | B. Pandey (QA Lead) | 2026-08-14
ST-04 | FR3 | Positive | Verify a customer can search and retrieve products using a combination of category and price range filters. | Multiple products exist across several categories and price points. | Filters: Category = 'Jewelry', Price = Rs. 500-2,000. | 1) Apply both filter criteria. 2) Submit search. | System returns only products matching both the category and price range, avoiding irrelevant results. | Correct filtered results returned. | Pass | B. Pandey (QA Lead) | 2026-08-14
ST-05 | NFR2 | Positive | Verify the system responds to a product-search request within an acceptable time under normal load. | Catalog contains at least 500 sample product records. | Search term: 'scarf' | 1) Submit search. 2) Measure response time. | Result is displayed within 3 seconds, per the response-time target in NFR2. | Result displayed in 1.6 seconds. | Pass | B. Pandey (QA Lead) | 2026-08-14
ST-06 | NFR1, FR11 | Negative | Verify an unauthenticated user attempting to access the Order History page directly (bypassing login) is denied access with a clear message. | User is logged out; no active session. | User manually enters the direct URL of the Order History page. | 1) Log out. 2) Paste the direct Order History URL into the address bar. 3) Press Enter. | User is redirected to the login page with the message 'Please log in to continue.' | User was redirected, but a generic error page appeared briefly before the login page loaded, instead of a clean redirect with the intended message. | Fail | B. Pandey (QA Lead) | 2026-08-14
ST-07 | NFR5 | Positive | Verify the scheduled nightly backup completes successfully and product/order data can be restored from it. | Backup job is scheduled to run at 1:00 AM daily on the staging environment. | Trigger the scheduled backup job manually for test purposes. | 1) Run backup job. 2) Restore the backup to a separate test instance. 3) Compare record counts. | Backup completes without error; restored instance record counts match the source exactly. | Backup completed; restored record counts matched exactly. | Pass | B. Pandey (QA Lead) | 2026-08-14
ST-08 | NFR7 | Positive | Verify core functions (search, cart, checkout) work correctly on both desktop Chrome and a mobile browser. | Chrome available on desktop and on a mobile device. | Perform search + add-to-cart on desktop; perform checkout on mobile Chrome. | 1) Complete search and add-to-cart on desktop. 2) Open cart and complete checkout on mobile. | All functions display and behave consistently on both devices with no layout or functional errors. | Both devices displayed and functioned consistently. | Pass | B. Pandey (QA Lead) | 2026-08-14

## User Acceptance Testing
QalaBazaar E-commerce Platform (QMS) - User Acceptance Testing
Test Case ID | Related Requirement | Scenario Type | Test Objective | Preconditions | Test Input | Test Steps | Expected Output | Actual Output | Status | Tester | Date Tested
UAT-01 | FR1 | Positive | A first-time customer registers an account unassisted, within an acceptable time. | Customer has received no formal training on the platform. | Real customer details (synthetic data used for testing). | 1) Customer completes registration unassisted, without help from the QA team. | Registration completed correctly within 3 minutes, without needing developer/QA assistance. | Completed in 2 minutes 30 seconds, unassisted. | Pass | R. Karki (Customer) | 2026-08-15
UAT-02 | FR5, FR6 | Positive | Customer adds a product to cart, checks out, and pays using their preferred payment method. | Customer logged in; product catalog available. | Add 1 item to cart; checkout using eSewa. | 1) Search product. 2) Add to cart. 3) Checkout and pay. | Order is placed and a confirmation is shown to the customer. | Order placed and confirmation displayed correctly. | Pass | R. KC (Customer) | 2026-08-15
UAT-03 | FR7 | Positive | Customer views the real-time status of their placed order. | Customer account exists with at least one active order. | Customer logs in and opens 'My Orders'. | 1) Log in as customer. 2) Open 'My Orders'. | Customer sees an accurate, up-to-date order status (e.g., Placed, Packed, Shipped). | Order status displayed accurately and matched the seller's update. | Pass | R. KC (Customer) | 2026-08-15
UAT-04 | FR2 | Positive | Seller adds a new product listing and manages existing inventory. | Seller account exists with listing permission. | Add product: 'Hemp Tote Bag', Price Rs. 950, Stock 15. | 1) Log in as seller. 2) Add the new product listing. | Product is saved and visible in the seller's product list, ready for customers to view. | Product saved and visible as expected. | Pass | K. Maharjan (Seller) | 2026-08-15
UAT-05 | NFR3 | Positive | A first-time seller lists a product relying only on the system's on-screen labels/prompts (no formal training). | New seller has not used the platform before; given no instruction beyond login credentials. | Same product details as TC-A-04. | 1) New seller attempts to add a product independently. | Seller completes the task without asking for help, indicating the interface is intuitive (NFR3). | Task completed independently in 5 minutes with one brief pause to locate the 'Publish' button. | Pass | K. Maharjan (Seller) | 2026-08-15
UAT-06 | FR11, NFR1 | Positive | Customer logs out at the end of a session and confirms the session is fully closed. | Customer is logged in. | Click 'Logout'; then reopen the browser tab. | 1) Click Logout. 2) Reopen a new tab and navigate to the platform URL. | User is prompted to log in again; no order or account data is visible without re-authentication. | Login prompt shown; no data visible without logging in again. | Pass | R. Karki (Customer) | 2026-08-15
UAT-07 | FR6 | Negative | Customer attempts to purchase an item that just went out of stock. | An item's last unit was purchased by another customer moments earlier. | Customer selects the same item and attempts to check out. | 1) Attempt to complete checkout for the now out-of-stock item. | System prevents the purchase and clearly explains why, suggesting similar available products. | Purchase was correctly prevented, but the on-screen message only said 'Unable to complete order' without explaining why or suggesting alternatives. | Fail (Minor) | R. Karki (Customer) | 2026-08-15
UAT-08 | NFR4 | Negative | Customer attempts to browse and place an order during a simulated maintenance window. | Platform maintenance window is simulated for 2:00 AM-2:30 AM. | Attempt to place an order during the simulated maintenance window. | 1) Attempt the checkout action with the system clock/test flag set to the maintenance window. | System either restricts the action per policy or clearly states the platform is under maintenance, with an estimated return time. | Action was restricted as expected, with a message stating the maintenance window and expected return time. | Pass | K. Maharjan (Seller) | 2026-08-15

## summary
QalaBazaar - Test Execution Summary
By Test Level
Test Level | Total | Pass | Fail | Pass Rate
Unit | 10 | 8 | 2 | 80%
Integration | 8 | 7 | 1 | 87.5%
System | 8 | 7 | 1 | 87.5%
UAT | 8 | 7 | 1 | 87.5%
Total | 34 | 29 | 5 | 85.29%
By Scenario Type
Test Level | Total | Pass | Fail | Pass Rate
Positive | 22 | 22 | 0 | 100%
Negative | 12 | 7 | 5 | 58.33%
" |  |  |  |  | ] | \
Pass | 29
Fail | 5